## Sprint-1
Sprint Plan 1
issues | User stories /Task title | Story points | Associated tasks/Task description | Priority | Risk | Assign | Due date
#2 | US.1: Create Home Page (User can access the website) | 2 | Task.1: Create Home Page layout, can see site name, create account, login Task 2:Navigation bar, have buttons that access different functions | Medium: Having the pages ready for other members to work on is important and gives the members an idea of how the site should be | Low: While having a visual representation of how the site should look like is essential, others can still work on functionality without the home page | Richard / Nesrine | 2024-09-29
#3 | IS.2: Create Student Page View | 5 | Task.1: Show student id as an indicator of who's logged in Task 2: Show the buttons available to them (Logout) Task 3: Show list of all students with id,firstname,lastname, and team assigned to them | Medium: This task is a mandatory criteria for this project, however this issue is mainly for the visual aspects. | Low: The page view does not interfere with other components/pages. | Richard/ Vladimir / Nesrine | 2024-09-29
#4 | IS.3: Implement Site name and Logo | 2 | Task.1: Integrate the site name and logo into the header of each page | Low: Important for consistent branding but not critical to core functionality. | - Low:​ ​Inconsistent branding could lead to user confusion. ​ - Poor logo placement might affect aesthetic appeal. | Nesrine | 2024-09-29
#5 | IS.4: Add CSS to pages | 3 | Task.1: Apply CSS styles to ensure a consistent and responsive design across all web pages. Task.2: Focus on accessibility and cross-browser compatibility. | Medium: - Enhances user experience but is not immediately critical. | Low: - Poor design choices may negatively impact user experience. - Inconsistent styling could lead to brand misrepresentation. | Nesrine/Richard/ Vladimir | 2024-09-29
#6 | US.2: Create account function (User can create a roled account (student/Instructor)) | 8 | Task.1: Develop functionality for user account creation. Task.2: Implement form validation for input fields. Task.3:Ensure secure storage of user credentials. | High: -Essential for user interaction and access | High: Need to differentiate which type of user is logged in. Which will be used for Instructor function | Richard/ Vladimir / Nesrine | 2024-09-29
#7 | US.3: Login verification (User can login with his account) | 8 | Task.1: Implement secure login verification processes. Task.2﻿: Use encryption for password storage and transmission. Task.3: Include error handling for failed login attempts. | High: Vital for security and user access control. | High: Security breaches could compromise user data | Jimmy | 2024-09-29
#8 | IS.7: Create 2 Database Tables to store user login information | 3 | Task.1: Set up tables to store user login information securely. Task.2: Design schema to optimize query performance. Task.3:Implement backup and recovery procedures. | High: -Fundamental for data management and security. | Medium: Incorrect setup could lead to data integrity issues. | Vladimir/ Richard | 2024-09-29
#9 | IS.8: Create Database Table to store each team | 2 | Task.1: Design table schema for the teams table Task.2: Establish error handling | Medium: - Required for storing information about the teams | Medium: - Improper designs could cause issues down the road | Vladimir/ Richard | 2024-09-29
#10 | IS.9: Create Instructor Page View | 5 | Task.1:Display instructor-specific content and features. Task.2: Ensure data is presented in a clear and organized manner. Task.3: Allow instructors to filter and sort data as needed | Medium: - Key for instructor interaction and functionality | Meduim: Incorrect data display could lead to user frustration. | Vladimir/ Richard/ Nesrine | 2024-09-29
#11 | US.4: (Instructor) Create Team (User as an Instructor can create teams) | 5 | Task.1: Allow instructors to create teams within the system. Task.2: Validate team creation inputs for accuracy. Task.3: Provide feedback on successful team creation. | High: - Required for following user story 5 | Low: - As long as issue #8 is done correctly, then this step should be intuitive | Vladimir | 2024-09-29
#12 | IS.11: (Instructor) View Team | 3 | Task.1: Develop a feature for instructors to view team compositions. Task.2: Implement sorting and filtering options for better data management. Task.3: Ensure data is displayed in a user-friendly format. | High: - Essential for monitoring team dynamics and performance - Required for US4 & US5 | Medium: - Improper implementation could cause misinterpretation of the state of the actual data (database values) | Richard | 2024-09-29
#13 | US.5: (Instructor) Assign Student (User as an instructor can assign students to teams) | 5 | Task.1: Implement an interactible element in the instructor view Task.2: Develop an algorithm to select students and assign them to a team Task.3: Reflect the changes to the database table and provide feedback to the user | High: Essential for monitoring team dynamics and performance. | Meduim: Potential issues with data accuracy and display. | Victor | 2024-09-29
#14 | IS.13: Establish NodeJS Project Base | 2 | Task.1: Create a NodeJS Project Task.2: Configure settings to satisfy the requirements of other tools and services. | High: - Essential for every other step, otherwise there is no workspace | Medium: - Requires proper forethought into project requirements to determine the correct foundation | Richard | 2024-09-29
#15 | IS.14: Connect NodeJS to MySQL | 1 | Task.1:Set up NodeJS environment for backend development. Task.2:Install necessary packages and dependencies. Task.3:Configure server settings for optimal performance. | High: Fundamental for backend operations and development | Medium: - Improper setup could delay development processes | Jimmy/Richard | 2024-09-29
#16 | IS.15: Introduction Page View | 1 | Task.1:Design and implement an introductory page view for users. | Low: Useful for first impressions but not critical to functionality | Low: Minimal risk if content is static. | Nesrine | 2024-09-29
#17 | IS.16: Hosting MySQL a Database Host | 1 | Task.1: Set up and configure MySQL database hosting. Task.2: Ensure secure access and backup procedures. | Medium: Essential for data storage and management. | Medium : - Potential for data loss if not configured properly. | Vladimir | 2024-09-29
#18 | IS.17: Add React routing for pages | 1 | Task.1: Implement React Router to manage navigation within the application Task.2:Ensure that all pages are accessible through defined routes. Task.3: Support dynamic routing for future scalability. | High: - Important for user navigation and experience. | Medium : - Incorrect routing setup could lead to navigation errors. | Nesrine | 2024-09-29
#19 | IS.18: Add page common components | 1 | Task.1:Develop reusable components (e.g., headers, footers, buttons) to ensure uniformity in design and functionality. Task.2: Integrate these components across all pages to maintain a consistent user interface. | High: Enhances design consistency | Medium : - Inconsistent styling may arise if components are not standardized, affecting the overall look and feel. - Potential for increased maintenance if components are not properly documented, leading to technical debt. - Complexity in integrating components with existing code could lead to unexpected bugs. | Nesrine | 2024-09-29
#20 | IS.19: Create tokens to store login info | 2 | Task 1: Store information of logged in user onto the local storage. Task 2: Output user_name of logged in user | High: Without tokens, users can't determine who is logged in | High: Need to differentiate which type of user is logged in. Which will be used for Instructor function (issue #10,11,12) | Richard | 2024-09-29
#21 | IS.20: Add Authentication Middleware to Protect Routes for Logged-In Users | 5 | Task 1: Take token stored based off of logged in user. Task 2: Implement authorization for students and instructor to allow them to see pages and data | High: Necessary to provide users correct access to pages allowed. Other wise users can acesss pages by inputting a specific path in the url path | Low: Does not affect other functionality of project and be worked on independently | Teodor | 2024-09-29
#22 | US.6: Functioning Logout feature (User can logout of their accounts) | 5 | Task 1 : Implement functionality to the logout button to delete any saved tokens and allow users to re-login/create a new account | Low: - Not vital, but very welcome for testing different user logins | Medium: - Incorrect implementation could cause a security leak (in a public setting) | Teodor | 2024-09-29