## Sheet1
Sprint Plan 4
ISSUES | USER STORY ¦ TASK TITLE | STORY POINTS | DUE DATE | DESCRIPTION / ASSOCIATED TASKS | PRIORITY | RISK | RESPONSIBLE
#32 | Task.32 Create the peer review confirmation page | 1 | 2024-11-23 | Task 59 Create Peer Review Button Task 60 Create Summary of Details and Detailed UI Buttons Task 61 Enable Instructor Authorization AT #75 | Medium | Low | Richard
#81 | US.78 As a user I wish to view the Summary of details and sort them in ascending/descending order per column | 7 | 2024-11-25 | Issue Tracking Task.62 Create Student Peer Review Tables #62 Task.97 Sorting Summary Review Columns #100 Acceptance Test Acceptance Test (AT) 4.1 - US.78 As a user I wish to view the Summary of details and sort them in ascending/descending order per column #93 Unit Test Unit Test (UT) 4.0 Sorted review criteria's #90 | High | Low | Richard
#82 | US.79 As a user logged in as a student, I want to be able to undo a review I submitted on a student | 4 | 2024-11-26 | Issue Tracking Create a Delete Review button Task.80 Create a Delete Review Button #83 Button is next to the student the reviewer already submitted a review to that prompts the user if they wish to confirm deletion Create query to remove student's review Task.81 Create a query to remove a student's review #88 Using a POST call, knowing the user's id or anything associated, request to remove the associated author's review Create review deletion prompt Task.82 Create a review deletion prompt #89 User gets alerted that the review has been removed AT tracking Acceptance Test (AT) 4.0 - US.79 As a user logged in as a student, I want to be able to undo a review I submitted on a student #92 Unit Testing Unit Test (UT) 4.1 Review deletion #91 | High | Low | Teodor
#83 | Task.80 Create a Delete Review Button | 1 | 2024-11-24 | US.79 As a user logged in as a student, I want to be able to undo a review I submitted on a student #82 Button is next to the student the reviewer already submitted a review to that gives a prompt after clicking if they wish to confirm deletion | Low | Low | Teodor
#88 | Task.81 Create a query to remove a student's review | 2 | 2024-11-25 | US.79 As a user logged in as a student, I want to be able to undo a review I submitted on a student #82 Button is next to the student the reviewer already submitted a review to that gives a prompt after clicking if they wish to confirm deletion | High | Low | Teodor
#89 | Task.82 Create a review deletion prompt | 1 | 2024-11-26 | US.79 As a user logged in as a student, I want to be able to undo a review I submitted on a student #82 User gets alerted that the review has been removed | Low | Low | Teodor
#90 | Unit Test (UT) 4.0 Sorted review criteria's | 1 | 2024-11-25 | User Story 57 Display a table that showcases each student the instructor can see with the following columns Student ID ¦ Last Name ¦ First Name ¦ Team ¦ Cooperation ¦ Conceptual ¦ Practical ¦ Work Ethic ¦ Average ¦ Peers who responded | Medium | Low | Richard
#91 | Unit Test (UT) 4.1 Review deletion | 1 | 2024-11-26 | User Story 57 Retrieve the the information required for all student's columns and display them on the table Using our existing GET api calls, gather the data necessary and print them onto the table with their respective columns | Medium | Low | Victor/Nesrine
#92 | Acceptance Test (AT) 4.0 - US.79 As a user logged in as a student, I want to be able to undo a review I submitted on a student |  | 2024-11-27 | Issue Tracking #82 User Acceptance FI User is logged in as a student User has already submitted a review on a student User clicks "Undo review" User removes their remove on the student they clicked "Undo Review for" | Low | Low | Richard
#93 | Acceptance Test (AT) 4.1 - US.78 As a user I wish to view the Summary of details and sort them in ascending/descending order per column |  | 2024-11-28 | Issue Tracking This AT is for #81 User Acceptance FI User is logged in as an instructor User is under the View Summary Reviews tab User is able to see the summary of all student reviews User can click any of the four criteria of the submitted reviews and sort them by clicking the title of any criteria | Low | Low | Richard
#94 | Unit Test (UT) 4.2 Detailed Team Reviews | 1 | 2024-11-23 | Issue Tracking Unit Test for User Story #58 Configure project to run test when calling "npm test" on client side Check 3 instance where it should fail No reviews found for the existing team No team found with mocked group_id in the test No reviews for an individual member with a mocked username from database Use mockJest, axios, and other to compose the unit test | Medium | Low | Vladimir
#95 | Task.83 Fix Home Page/Header css | 2 | 2024-11-24 | The web application home page requires a slight revamp Remove the Navigation bar for all pages Log out button: Move Logout button onto the header Hide Log out button when user is not logged in Display Log out button when user is logged in Readjust home page visuals (text fonts, colors and element sizes) Improve/Fix Login and Create Account static responsiveness on different screen sizes | Low | Medium | Vladimir
#96 | Task.96 Incorporate Code Analysis Tools | 4 | 2024-11-26 | Find a static code analysis tool and figure out a way to incorporate it into our project Install it within the project Fix bugs and code smells (explaining why they've been fixed) Create quality gates in the CI/CD pipeline (Maybe?) Suggestions: ESLINT, STYLELINT | Medium | Medium | Jimmy
#97 | Task.97 Sorting Summary Review Columns | 4 | 11-25-2024 | Issue Tracking US.78 As a user I wish to view the Summary of details and sort them in ascending/descending order per column #81 Upon clicking a column "Student ID ¦ Last Name ¦ First Name ¦ Team ¦ Cooperation ¦ Conceptual ¦ Practical ¦" it will sort in ascending/descending in that order | High | Medium | Richard