## Sheet1
Sprint Plan 2
ISSUES | USER STORY ¦ TASK TITLE | STORY POINTS | DUE DATE | DESCRIPTION / ASSOCIATED TASKS | PRIORITY | RISK | RESPONSIBLE
#27 | Task.27 Add Authentication Middleware to Protect Routes for Logged-In Users | 5 | 2024-10-18 | Users who aren't logged in should not be able to access pages directly through the url. Logging in gives authorization to see Student_View.jsx page and Instructors should only see Instructor_View.jsx page | High | Medium | Teodor
#28 | Task.28 Functioning Logout feature | 5 | 2024-10-18 | Create functionality for the logout button | Medium | Medium | Teodor
#30 | US.30 While Logged In as a Student, I shall be able to view my teammates through an interface and select one of them for a peer review | 9 | 2024-10-26 | Task.36 Create a team interface Task.39 Peer Review Selection Task.41 Pass Selected Team Member | High | Medium | Vladimir
#31 | US.31 As a Student, I shall be able to review a teammate based on select criteria's with a grading scheme of 1-5 and have the option of adding a comment for each criteria | 12 | 2024-10-20 | Task.34 Create a peer review table for the database Task.33 Create the peer review page Task.32 Create the peer review confirmation page Task.35 Record peer review submission data into the database | High | High | Jimmy/ Nesrine
#32 | Task.32 Create the peer review confirmation page | 1 | 2024-10-13 | This issue is part of US.31 1. Create a new page with path /Peer_Review_Confirmation 2. Provide feedback from the submission (whether it recorded the review or not) 3. Allow the user to return to the Student View Page | Medium | Low | Nesrine
#33 | Task.33 Create the peer review page | 6 | 2024-10-13 | This issue is part of US.31 1. Create a new page with path /Peer_Review 2. Add a form table that will allow the user to rate the assessment fields: Cooperation, Conceptual Contribution, Practical Contribution and Work Ethic, this table will use radio buttons to define a 1-5 rating scale (required) 3. Add optional comment areas for each field 4. Add a submission button that will record all this information to the database through an endpoint and redirect the user to the confirmation page | High | Medium | Jimmy
#34 | Task.34 Create a peer review table for the database | 3 | 2024-10-13 | This issue is part of US.31 1. Plan out the schema and DDL script 2. Create the table in MySQL 3. Record the schema & DDL script for future reference | High | High | Vladimir
#35 | Task.35 Record form submission data into the database | 3 | 2024-10-13 | This issue is part of US.31 1. Create a new back-end endpoint 2. Capture all information submitted from the Peer Review Page 3. INSERT the information into the new database table for peer reviews 4. Verify whether the entry was successfully inserted | Medium | Low | Vladimir
#36 | Task.36 Create a team interface | 5 | 2024-10-16 | 1. Create a react component visible to Students that will provide as the team interface 2. Create a view inside interface that will list a number of students 3. Query the database to retrieve only the name of the students that are part of the same team as the logged in user 4. Display the results of the query into the interface in a list | Medium | Medium | Vladimir
#48 | Acceptance Test (AT) 1.0: Task.04 Create Account Function | 3 | 2024-10-26 | Issue Tracking This acceptance test is for #4 User Acceptance User fills out Create Account form If user submits empty data, then a requirement error will show up indicated to fill in the required field User submits Create Account form User gets a confirmation that the account was created successfully | Medium | Low | Jimmy/Richard
#50 | Acceptance Test (AT) 1.1: Task.07 Login verification #07 | 3 | 2024-10-26 | Issue Tracking This acceptance test is for #7 User Acceptance FI User fills in login form If user submits empty data, then requirement error message will show up If user inputs invalid login information then error message will show up User submits login form User will see the student view page or instructor view page depending on user's login information | Medium | Low | Jimmy/Richard
#39 | Task.39 Peer Review Selection | 3 | 2024-10-23 | This issue is part of US.30 This issue is dependent on Task.36 1. In the team interface, implement a way to select/click an entry 2. This can be done as a button, link, label, etc... 3. Upon selecting another student (should be a team member, if Task.36 was done properly), the user should be redirected to the Peer Review Page | High | Low | Vladimir
#40 | Task.40 Fix CSS styling for all elements | 3 | 2024-10-26 | The current model of the site does not have a dynamic window. All elements should be visible regardless window size. | Low | Low | Nesrine
#41 | Task.41 Pass selected team member | 1 | 2024-10-23 | This issue is part of US.30 This issue is dependent on Task.39 1. Upon selecting a team member, save the selected team member's name to a variable 2. Upon redirection, send the team member's name as a prop to the peer review page | Medium | Low | Richard
#44 | Task.44 Implement the CI/CD Pipeline | 3 | 2024-10-25 | 1. Establish the github pipeline 2. Connect the project to the github pipeline 3. Connect the database to the github pipeline 4. Verify whether the pipeline is functional | Medium | Medium | Jimmy
#12 | Task.12 Assign Student | 2 | 2024-10-23 | 1. Display Team Assigned on Student View2. Connect the project to the github pipeline 3. Connect the database to the github pipeline 3. Add functionality to assign Students seperately to a group | High | High | Victor / Vladimir