## Sheet1
Sprint Plan 3
ISSUES | USER STORY ¦ TASK TITLE | STORY POINTS | DUE DATE | DESCRIPTION / ASSOCIATED TASKS | PRIORITY | RISK | RESPONSIBLE
#56 | US.56 As an instructor, I want to access the Summary of Details and Detailed Results of my students | 1 | 2024-11-05 | Task 59 Create Peer Review Button Task 60 Create Summary of Details and Detailed UI Buttons Task 61 Enable Instructor Authorization AT #75 | High | Medium | Richard/Vladimir
#57 | US.57 As an instructor, I want a summary of all the student's individual review scores | 5 | 2024-11-08 | Task 62 Create Student Peer Review Tables Task 63 Retrieve Summary of Details Data AT #76 | High | Medium | Richard
#58 | US.58 As an instructor, I want to be able to see Detailed Results of the students I can see | 5 | 2024-11-08 | Task.64 Design Detailed View UI Task 65 Retrieve Detailed Results data AT #77 | High | Medium | Vladimir/Richard
#61 | Task.61 Enable Instructor Authorization | 8 | 2024-11-09 | User Story 56. Enable instructor only authentication to all instructor sites To prevent users from typing onto the url to access pages, authentication is required to load the desired pages only if you are an instructo | High | Low | Teodor
#59 | Task.59 Create Peer Review Button | 1 | 2024-11-04 | User Story 56. Create a new button called "Peer Reviews" on the instructor view page This button will be used to access a new page called "peer_reviews" and two new buttons will be present | Low | Low | Richard/Jimmy
#60 | Task.60 Create Summary of Details and Detailed UI Buttons | 1 | 2024-11-04 | User Story 56 Create two new buttons called "Summary of details" and "Detailed Results" These two buttons will be only visible in /instructor/peer_reviews Just like the main instructor view page the two buttons will not load a new page but show new content based on the button pressed (similar to the main instructor page when clicking "View Teams" "View Students" "Create Team") | Low | Low | Richard/Jimmy
#62 | Task.62 Create Student Peer Review Tables | 3 | 2024-11-07 | User Story 57 Display a table that showcases each student the instructor can see with the following columns Student ID ¦ Last Name ¦ First Name ¦ Team ¦ Cooperation ¦ Conceptual ¦ Practical ¦ Work Ethic ¦ Average ¦ Peers who responded | Medium | Low | Richard
#63 | Task.63 Retrieve Summary of Details Data | 8 | 2024-11-07 | User Story 57 Retrieve the the information required for all student's columns and display them on the table Using our existing GET api calls, gather the data necessary and print them onto the table with their respective columns | High | Low | Richard
#64 | Task.64 Design Detailed View UI | 1 | 2024-11-07 | User Story 58 Create a table that displays Team Name: _________ Student Name:_______ Then the following columns: Member ¦ Cooperation ¦ Conceptual ¦ Practical ¦ Work Ethic ¦ Average Across All Each student that reviewed this student will appear here in each row The same student who left a review, will have their comments displayed here with the corresponding criteria ex: Student X (Cooperation ): _____________________ | Medium | Low | Vladimir
#65 | Task.65 Retrieve Detailed Results data | 8 | 2024-11-07 | User Story 58 Using our existing GET calls, retrieve the required data and display it onto the table Acceptance Test | High | Low | Vladimir
#66 | Unit Test (UT) 1.0 - Account Creation Test | 5 | 2024-11-09 | UT For User Story #4 Create a unit test for feature "Account Creation" Use jest to create a unit test Use ARRANGE, ACT, ASSERT Test the feature in cases it would succeed Test the feature in cases it would fail | Medium | Low | Nesrine
#67 | Unit Test (UT) 1.1 - Login Test | 3 | 2024-11-09 | Create a unit test for the login feature #7 Configure the project to run tests when calling npm test Check for instances where it should fail Optional (Use Jest or a different unit testing framework) Use ARRANGE, ACT, ASSERT to make it easier to compose the test | Low | Low | Jimmy
#69 | Unit Test (UT) 1.2 - View Team | 5 | 2024-11-09 | UT For User Story #11 Create a unit test for feature "View Team" Use jest to create a unit test Use ARRANGE, ACT, ASSERT Test the feature in cases it would succeed Test the feature in cases it would fail | Medium | Low | Nesrine
#68 | Unit Test (UT) 1.3 - Team Creation Test | 5 | 2024-11-09 | UT For User Story #10 Create a unit test for feature "Team Creation" Use jest to create a unit test Use ARRANGE, ACT, ASSERT Test the feature in cases it would succeed Test the feature in cases it would fail | Medium | Low | Nesrine
#75 | Acceptance Test (AT) 3.0 - US.56 Access of Summary of Details and Detailed Results | 1 | 2024-11-09 | US 56 User signed in as an instructor User can see Summary of Details button & Detailed Results button User can click these buttons and the associated table renders in | Medium | Low | Richard
#76 | Acceptance Test (AT) 3.1 - US.57 Summary of individual student results | 1 | 2024-11-09 | US 57 User is already logged and and has clicked "Summary of Details" button User is able to see all the students who have received a peer assessment. User can easily see the total average of each criteria for a student, their information (id , first and last name, peers who responded) | Medium | Low | Richard
#77 | Acceptance Test (AT) 3.2 - US.58 Detailed Results of students | 1 | 2024-11-09 | US 58 User is already logged and and has clicked "Detailed Results" button User is able to see a List of Teams User can click "View Peer Results" User sees the teams who have students and have received peer reviews. if no reviews are present then a message "No reviews for this member" will appear if a team has no students then a message "No reviews found for this team." will appear User sees students name followed by author of reviews and the grades given followed by comments (insights) if no comment exists then a message "No comment" is automatically printed instead. | Medium | Low | Richard